### WORK PACKAGE 3

### Key indicators and response in relation to typology for macrophytes

Detailed workplan

### Objectives

The objectives of WP3 are:

- to determine the factors that regulate macrophyte communities and their temporal stability at local and regional scale

- to determine long-term changes in macrophyte communities in the Baltic Sea area

- to define macrophyte indicators that adequately describe the state of coastal ecosystems

- to define reference conditions for macrophyte communities, i.e. the status of vegetation under ‘pristine’ conditions, in different areas of the Baltic Sea.

##### DELIVERABLES

- (No. 3) Quality controlled data sets for macrophytes.

- (No. 15) Small-scale vegetation models.

- (No. 20 & 32) Reference conditions for benthic vegetation. Draft (No. 20) and final version (No. 32).

- (No. 25) Large-scale vegetation models.

- (No. 30) Definition of vegetation indicators.

- (No. 31) Verified typology for vegetation (i.e. identification of the status of vegetation indicators in different type areas).

- (No. 34) Monitoring recommendations for vegetation in the Baltic coastal zone.

##### HYPOTHESES

We hypothesise that:

- Water quality, temperature, salinity, insolation, exposure, icecover and geomorphology (substratum, coastal slope) are important regulators of the distribution and abundance of macrophytes.

- The relative importance of the various regulating factors changes with the scale of study. Thus, insolation, temperature, ice-cover and salinity change across large spatial scales and are likely to regulate large-scale patterns of distribution and abundance of macrophytes across the Baltic distribution range. At the local scale, exposure, substratum and coastal slope change from site to site, and are likely to play an important regulating role together with secondary gradients in water clarity, nutrient concentrations and salinity.

- Short- and long-term changes in distribution and abundance differ among macrophyte species due to differences in susceptibility to changing water quality and differences in colonisation capacity.

- Robust key indicators of vegetation can characterise the ecological state of coastal waters.

- Reference conditions for selected key parameters can be identified based on historical records and/or models relating the key parameters to anthropogenic pressure.

##### WORKPLAN

We have organised the work as illustrated by the flow diagram below.

Flow diagram of work plan and deliverables for work package 3. More boxes behind each other illustrate that parallel analyses are made by several partners. Dashed lines indicate that the deliverables are part of a larger deliverable.

DETAILED DESCRIPTION OF DELIVERABLES

All CHARM partners are responsible for data compilation, quality assurance and establishment of metadata (Del. 2)– even the partners not actually engaged in WP3. All partners engaged in WP3 are further responsible for the tasks connected with the vegetation in their respective area, i.e. small-scale data analyses, definition of reference conditions, identification of vegetation indicators and definition of typology (Del. 8, 12, 17-20). In addition, some partners are responsible for large-scale analyses of vegetation data (Del. 14, Table 1). The participating and responsible persons from each institution are indicated in Table 2:

Each partner sends completed inputs to NERI, who is then responsible for compiling the inputs and finalising all deliverables within this work package.

Table 1. Responsibility of each partner in the various deliverables.

|  | NERI (1) | FEI (2) | AAU (3) | CORPI (5) | IOW (6) | EMI (7) | IAE (8) | SUSE (9) | MIR (10) | EMAUG (11) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| person-months per partner: | 24 | 11 | 8 | 3 |  | 9 | 4 |  | 4 | 15 |
| Deliverable 2 |  |  |  |  |  |  |  |  |  |  |
| - Datacompilation & QA | X | X | X | X | X | X | X | X | X | X |
| - Quality assurrance | X | X | X | X | X | X | X | X | X | X |
| - Metadata | X | X | X | X | X | X | X | X | X | X |
| - Evaluation of comparability | X |  |  |  |  |  |  |  |  |  |
| Deliverable 8 |  |  |  |  |  |  |  |  |  |  |
| - Small scale veg. models | X | X | X | X |  | X | X |  |  | X |
| - Actual and historic state | X | X | X | X |  | X | X |  |  | X |
| Deliverable 12 |  |  |  |  |  |  |  |  |  |  |
| - Reference conditions | X | X | X | X |  | X | X |  |  | X |
| Deliverable 14 |  |  |  |  |  |  |  |  |  |  |
| - Large-scale models | X | X | X |  |  | X |  |  |  | X |
| Deliverable 17 |  |  |  |  |  |  |  |  |  |  |
| - Id. of indicators | X | X | X | X |  | X | X |  |  | X |
| Deliverable 18 |  |  |  |  |  |  |  |  |  |  |
| - Verified typology | X | X | X | X |  | X | X |  |  | X |
| Deliverable 19 |  |  |  |  |  |  |  |  |  |  |
| - Verified reference con. | X | X | X | X |  | X | X |  |  | X |
| Deliverable 20 |  |  |  |  |  |  |  |  |  |  |
| - Recommendations | X | X | X | X |  | X | X |  |  | X |

Table 2. Persons from each institution participating and/or responsible for work in WP3.

| Institution | Person | Participant | Responsible |
| --- | --- | --- | --- |
| NERI | Dorte Krause-Jensen | X | X |
|  | Kurt Nielsen | X |  |
| FEI | Saara Bäck | X | X |
|  | Ari Ruuskanen | X | X |
| AAU | Erik Bonsdorff | X | X |
| CORPI | Sergei Olenin | X | X |
|  | Darius Daunys | X |  |
| IOW | Gerald Schernewski | X | X |
| EMI | Georg Martin | X |  |
|  | Kaire Torn | X | X |
| IAE | Andris Andrusaitis | X | X |
| SUSE | Sif Johansson | X | X |
| MIR | Jan Warzocha | X | X |
| EMAUG | Hendrik Schubert | X | X |
|  | Sigrid Sagert | X |  |

The deadlines of deliverables are indicated in Table 3. The internal deadline

is the deadline for the partners to send input to the WP-responsible (Dorte Krause-Jensen), PL-deadline is the deadline for the WP-responsible to send the deliverable to the project leader (Trine Christiansen) and the EU deadline is the deadline for the project leader to send the deliverable to EU.

Table 3. Deadline for deliverables

|  | Internal deadline | PL-deadline | EU-deadline |
| --- | --- | --- | --- |
| Deliverable 3 | 15 Apr-02 | 15 May-02 | 01 June-02 |
| - Datacompilation & QA |  |  |  |
| - Metadata |  |  |  |
| Deliverable 15 | 01 July-03 | 15 July-03 | 01 Aug-03 |
| - Small scale veg. models |  |  |  |
| - Actual and historic state |  |  |  |
| Deliverable 20 | 01 Nov-03 | 15 Nov-03 | 01 Dec-03 |
| - Reference conditions |  |  |  |
| Deliverable 25 | 01 May-04 | 15 May-04 | 01 June-04 |
| - Large-scale veg. models |  |  |  |
| Deliverable 30 | 01 Nov-04 | 15 Nov-04 | 01 Dec-04 |
| - Id. of veg. indicators |  |  |  |
| Deliverable 31 | 01 Nov-04 | 15 Nov-04 | 01 Dec-04 |
| - Verified typology |  |  |  |
| Deliverable 32 | 01 Nov-04 | 15 Nov-04 | 01 Dec-04 |
| - Verified reference con. |  |  |  |
| Deliverable 34 | 01 Nov-04 | 15 Nov-04 | 01 Dec-04 |
| - Recommendations |  |  |  |

A detailed description of each deliverable follows below:

Deliverable 3: “Quality controlled data sets for macrophytes”

Nature of deliverable: The deliverable is a short report (Da) with a summary of main findings, methods and data. The report will contain the metadata and information on methods and quality assurance supplied by each partner. The level of comparability of data will be summarised by the task manager.

The deliverable contains the following tasks:

- Compilation of data and construction of metadata: Each partner compiles recent and historic data on macrophytes and coupled physico-chemical parameters from local areas of the Baltic Sea.

The relevant vegetation parameters and physico-chemical parameters are defined in the ‘data-compilation template’  (see excel-file: template.xls) and in the metadata-template (Appendix 1).

For small-and large scale vegetation analyses it is important that vegetation data and physico-chemical data are linked at the finest possible scale, i.e. preferably at station-level. As a consequence, if physico-chemical conditions are measured near the vegetation station, the station id. for the physico-chemical data should be indicated. For each dataset it should also be indicated which area (like estuary or embayment) the dataset belongs to (see Appendix 1 and the excel-file: template.xls).

Each partner makes the local vegetation data and coupled physico-chemical data be available electronically. The compiled data should be organised in spread sheets using columns as defined by the ‘data-compilation template’ (excel-file: template.xls).

All compiled data should be matched by a metadata description using the metadata template (Appendix 1). Preferably all compiled data should be available electronically, but if some material is available only in printed form, this material should still be included in the metadata description with the notification that the data are available only on print.

- Quality assurrance: Each partner takes the following steps in quality assurrance of local vegetation data:

- Ensures that the nomenclature of macroalgal species follows Nielsen et al. (1995).The nomenclature of marine angiosperms should also follow specified guidelines. For seagrasses, the latest taxonomic guide is by Kuo & Den Hartog (2001).

- Ensures that the selected data are of acceptable quality for local analyses. Thus, metadata sheets and worksheets with compiled data should be made only for data of acceptable quality.

- Checks whether documentation and intercalibration of the methods exist

- Metadata: Each partner produces metadata, i.e. overview of the quality assured data regarding species, sites, sampling periods, frequency, vegetation parameters, chemical parameters and physical parameters as specified by the enclosed template (Appendix 1). The metadata allow an easy overview of the parameters available for analyses at local and regional scales.

The metadata should be followed by a short description of sampling methods/ experimental methods used in the compiled data set and by information on the level quality assurance.

Also, available information on local vegetation indicators already in use is most welcome. Such information can inspire the further analyses.

- Evaluation of comparability: Based on the metadata, the workpackage responsible evaluates which vegetation parameters and physico-chemical parameters are available to allow a series of comparable small-scale analyses and which data sets allow large scale analyses. The evaluation includes:

-  	Taxonomic level of comparability e.g. species / genus/ functional groups

- Comparability of vegetation parameters: e.g. presence/ absence, cover, biomass

- Comparability of physico-chemical parameter

- Temporal and spatial scale of comparability

The success of WP3 depends on the quality and comparability of existing data. Macrophyte data are likely to be most comparable at the local scale while differences in methods, intensity, scale and extension of sampling may cause difficulties in performing comparative studies with historical data and large scale data analyses. In large-scale analyses and in comparisons with historic data, it might therefore be necessary to use a lower level of detail, e.g. compare relative importance of functional groups and common, well-documented key species instead of doing comparisons at species level.

Another crucial point can be to obtain reliable relationships between macrophyte characteristics and environmental factors. These analyses require that there are available physico-chemical data representing the stations where vegetation surveys are performed. While recent data often include these aspects, early studies rarely do. We may therefore need to use indirect data (e.g. increase in use of fertilizers during the last 50 years) to suggest the cause of long-term changes.

The evaluation leads to a priority list of parameters to analyse at small and large scales (Deliverables 15 and 25). Based on the considerations above, it is likely that there may be 2 types of comparable data sets:

-	Detailed datasets from few areas (for local data analysis).

- 	Coarse data sets from many areas (for regional data analysis or for evaluating long term changes).

Deliverable 15: “Small-scale vegetation models”

Nature of deliverable: The deliverable is a method development (Me). NERI compiles the report based on completed inputs from each partner on methods, results and discussion regarding small-scale models and historic versus actual state of the vegetation.

The ultimate goal of both small and large scale vegetation analyses is to identify relations between vegetation parameters and anthropogenic impact.

This deliverable contains the following tasks

- Small-scale models: Each partner establishes small-scale models relating the vegetation parameters to regulating factors at local scales. The models should explain and predict changes in the distribution and abundance of vegetation in relation to changes in water quality and geomorphology. The analyses performed in the various local areas should be as parallel as possible. The models should, therefore, focus on the parameters included in the priority list of deliverable 3 and should – if possible - allow us to separate between “natural” and “anthropogenic” impacts on vegetation.

Initial analyses should involve correlations/regressions between potential vegetation indicators and each of the relevant physico-chemical parameters:

- Colonisation depth of key species (Zostera marina, Fucus vesiculosus) in relation to nutrient concentrations, light climate, salinity etc.

- Abundance (cover, biomass or shoot density) of key-species/groups (Zostera marina, Fucus vesiculosus, ephemeral macroalgae) at specific depths in relation to nutrient concentrations, light climate, salinity, exposure etc.

- Species number of macroalgae in coastal areas in relation to nutrient concentrations, light climate, salinity, exposure etc.

Results are illustrated by graphs and tables.

Possible further analyses may involve multiple regression analyses and/or further analyses of species diversity/composition in relation to physico-chemical factors. These analyses cannot be defined in advance but depend on the actual data.

- Historic and actual state of the vegetation: Based on the data compilation, each partner identifies the actual and historic state of the potential vegetation indicators and the extent of short- and long-term changes in the distribution and abundance of vegetation. Results are illustrated by graphs/maps.

Deliverable 20 and 32: “Reference conditions for benthic vegetation”.

- Draft (No. 20) and final version (No. 32).

Nature of deliverable: The deliverable is a short report (Re) integrating acquired knowledge. NERI compiles the report based on completed inputs from each partner on methods, results and discussion regarding reference conditions for benthic vegetation.

It is a prerequisite for the analyses, that WP1 provides input on typology, i.e. proposes which type areas to use.

Reference conditions should initially be defined for each type area based on results of deliverable 15: historical records and/or hindcasting based on small-scale models relating the key parameters to anthropogenic pressure. When using the hind-casting technique we should be aware that spatial gradients in vegetation indicators in relation to anthropogenic pressure do not necessarily imply similar temporal trends in relation to anthropogenic pressure.

The final version (No 32) may be adjusted based on the results of large-scale vegetation models (deliverable 25).

Deliverable 25: “Large-scale vegetation models”

Nature of deliverable: The deliverable is a method development (Me). NERI compiles the report based on completed inputs from FEI, AAU, EMI, and EMAUG on methods, results and discussion regarding large-scale vegetation models.

As for the small-scale analyses, the ultimate goal of the large-scale analyses is to identify relations between vegetation parameters and anthropogenic impact.

The large scale analyses should focus on the parameters of high priority defined in deliverable 3 and should also build on the information obtained in small-scale analyses.

Small scale-analyses may, for example show that the relation between a given vegetation parameter and a given anthropogenic parameter differs among local areas. Large-scale analyses might then identify whether such a difference can be attributed to large scale differences in e.g. salinity among the local areas.

Such broad scale relations should include initial correlations and regressions between the selected vegetation parameters and relevant physico-chemical parameters. Further analyses depend on the actual data.

Deliverable 30: “Definition of vegetation indicators”.

Nature of deliverable: The deliverable is a method development (Me). NERI compiles the report based on completed inputs from each partner.

Based on results of small and large-scale analyses, all WP3-partners define appropriate macrophyte indicators of the state of coastal ecosystems. An indicator is appropriate if it relates to anthropogenic impact in a predictable way and if reference conditions are well-established.

Deliverable 31: “Verified typology for vegetation”

(Input for typology work package)

Nature of deliverable: The deliverable is a short report (Re) integrating acquired knowledge. The information on benthic vegetation makes part of the over-all deliverable on typology.

We should evaluate whether the typology identified in WP1 makes sense with respect to macrophyte data.

Deliverable 34: “Monitoring recommendations for vegetation in the Baltic coastal zone”

Nature of deliverable: The deliverable is a short report (Re) integrating acquired knowledge. The information on benthic vegetation makes part of the over-all deliverable on monitoring recommendations.

NERI writes the report based on inputs on the following topics from each partner:

- Relevant physico-chemical parameters to include in a monitoring programme in order to evaluate changes in the vegetation

- Methods, frequency and time of sampling for the suggested indicators. The frequency of measurements should be related to the time scales of expected changes in the vegetation in relation to changes in water chemistry. References to available tests of methods and evaluations of sampling error are relevant in this context.

# Appendix 1

METADATA

| Where | Data set |
| --- | --- |
| Marine area |  |
| Estuary, coastal area |  |
| No. of sites/depth gradients |  |
| Latitude and longitude of depth gradients |  |
| When |  |
| Sampling years (19XX-XX) |  |
| Sampling months |  |
| Frequency (obs. per year) |  |
| Angiosperms (e.g. Zostera) |  |
| Species |  |
| Colonisation depths |  |
| Max. col. depth of meadows |  |
| Max. col. depth of isolated shoots |  |
| Depth of max abundance |  |
| Abundance at specific depths along gradients |  |
| Investigated depths |  |
| Biomass, below ground |  |
| Biomass, above ground |  |
| Shoot density |  |
| Cover |  |
| Area distribution |  |
| km2 seagrass cover |  |
| Macroalgae |  |
| Level of identification (species/genus/functional group) |  |
| Define the functional groups |  |
| Colonisation depths |  |
| Max. col. depth of individual species |  |
| Max. col. depth of deepest occurring macroalgae |  |
| Depth of max macroalgal abundance |  |
| Abundance at specific depths along gradients |  |
| Investigated depths |  |
| Biomass |  |
| Cover |  |
| Key algal species |  |
| Species (Fucus vesiculosus/Charophyceans) |  |
| Colonisation depths |  |
| Max. col. depth of key species |  |
| Depth of max key species abundance |  |
| Abundance at specific depths along gradients |  |
| Investigated depths |  |
| Biomass |  |
| Cover |  |
| Physico-chemical data |  |
| Id. of coupled water chemistry st. |  |
| Salinity |  |
| Inorganic nitrogen |  |
| Total nitrogen |  |
| Inorganic phosphorus |  |
| Total phosphorus |  |
| Exposure |  |
| Slope of coast line |  |
| Secchi-depth |  |
| Kt (m-1) |  |
| Proportion of hard substratum |  |
| Proportion of soft substratum |  |
| Duration of icecover |  |
| other factors |  |
| other factors |  |
| Reference: |  |
| Data type: rawdata/aggregated data |  |
| Data availability: electronically/printed |  |
| Comments: |  |

Methods used in the compiled dataset:

Level of quality assurance:

# Footnotes

Nielsen, R., Christiansen, Aa., Mathiesen, L. & Mathiesen, H. (1995) “Distributional index of the benthic macroalgae of the Baltic Sea area”. Acta Botanica Fennica 155:1-51.

Kuo, J. & Den Hartog, C. (2001)  “Seagrass taxonomy and Identification key”. Chapter 2 in Short, F.T. & Coles, R.G. (Eds.). Global Seagrass Research Methods. Elsevier.

# Text boxes

Verified typology

(deliverable 31)

Identification of vegetation indicators

(deliverable 17)

Definition of reference conditions

(deliverable 20, 32)

Id. of actual & historic state of vegetation & longterm changes

(deliverable 15)

Small scale vegetation models

(deliverable 15)

Metadata

and method description

(deliverable 3)

Compilation and QA of existing recent and historic vegetation data

(deliverable 3)

Rekommendations for monitoring vegetation

(deliverable 34)

Large scale vegetation models

(deliverable 25)